## High level Requirement Status
S.No | Activity/Fragment Name | Mockup Status | Confirmed by Customer | Layout Status | Code Status | Webservice
0 | Startup Screen | Ready | yes | done | done
1 | Login Form | Ready | yes | done | done
1.1 | Register Form | Ready | yes | done | done
1.2 | Forgot your password Form | Ready | yes | done | done
2 | Home Screen | Ready | yes | done | done
2.1 | Chat Screen | Ready | yes
2.2 | Settings Screen | Ready | yes
2.3 | About Distributor | Ready | yes
2.4 | Update Buyer/Retailer | Ready | yes
2.5 | Privacy Policy |  | yes
2.6 | Terms and conditions |  | yes
2.7 | Bugs or Feedback |  | yes
2.8 | Call Us |  | yes
3 | Checkout | Ready | yes

## Low level Requirement
E.No | Element | Type | Layout | Activity | Status
|  | Status |  | Type
|  | Started |  | Button
|  | Yet to start |  | Radio Button
|  | Hold |  | DropDown Listbox
|  | Finished |  | ListView
TextField
ActionBar Button
Back Button
TextBox